## Slide 1: Citizens Bank InSource of Appworks Education Finance and Personal Lending Data
Updated: January 26, 2021

## Slide 2
Appworks Background
Current & Future Responsibilities
Phase Definitions
  Phase 0: Prerequisites
  Phase 1: Options & Analysis
  Phase 2: Execute Option
  Phase 3: Decommission Sungard
Current Application Documentation
  High Level Application Blocks
  Student/PERL Conceptual Design
  Collocation Physical Diagram
    Dated diagram 2017
  Project & BAU Workflow
Tech Team Stakeholders
Next Steps
Appendices
Agenda

## Slide 3
Appworks Background
Entech provides a number of applications/services for Citizens that as a whole are commonly referenced as “Appworks”
  Student Lending – AOL
  Personal (PERL) Lending – AOL
  Lender Web
  Branch/Phone App
  School Certification
  Rate Quote Calculator
  Product Works
  Micro Works - Microsite management (~100 of microsites), lending marketing management
  HELOC landing page
  Document Management (Operational Service)
Appworks History
Pre 2013
  VTEK was original builder and owner of all system/equipment.
2013
  VTEK went out of business in 2013 and All1Team took over Appworks development and support in March 2013
2015
  Entech signed Assignment & Assumption of Agreements in Aug 2015
2020
  Entech legally changed its name to Anovaa
Appworks
Single instance supports 2 both PERL and Student
  Appworks Software is built, maintained and supported by Anovaa
    Responsive web design, web services, Oracle Single Node DB, SQL DB
    Jenkins, Crucible, Jira, Git
    Selenium for automated testing @Entech
  SunGard datacenters
    Prod @ Rancho Cordova, CA ; DR/UAT @ Scottsdale, AR
  Citizens owns all hardware, and owns partial right to the software
    Infrastructure is maintained by Entech
  Base technology stack: .net frameworks, Visual Studio, SOAP, ORACLE, SQL Server, 3rd party libraries/controls (Metadefender)
Current platform
  Frequent production and support issues
  Multiple identified open risk items
  Lack of desired business functionality
  Lack of vendor agility to respond to velocity of change requests
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters

## Slide 4
Area | Business | Anovaa | TS | 3rd Party (ParkPlace)
Business Analysis | X | X |  | 
Requirements | X |  |  | 
Software Development |  | X |  | 
Build and Deployment |  | X |  | 
Integration Testing |  | X |  | 
QA Testing | X |  |  | 
Project Management | X |  |  | 
Change Mgmt | X | X | X | 
Risk action items | X | X | X | 
Incident Management | X | X | X | 
Infra Support |  | X | X (consultancy) | X
Area | Business | Anovaa | TS | 3rd Party (ParkPlace)
Business Analysis | X |  | X | 
Requirements | X |  |  | 
Software Development |  |  | X | 
Build and Deployment |  |  | X | 
Integration Testing |  |  | X | 
QA Testing | X |  |  | 
Project Management | X |  | X | 
Change Mgmt | X |  | X | 
Risk action items | X |  | X | 
Incident Management | X |  | X | 
Infra Support |  |  | X | 
Current & Future Responsibilities
  Current Responsibilities
  Future Responsibilities
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters

## Slide 5
Phase Definitions
Phase 0 ~ Prerequisites
  Scope: Encompasses all the necessary groundwork required to enter into Phase 1 such as Anovaa
  Alignment, Resources, Project/POD Formation.
  Target Timeline: 4 – 6 Weeks
Phase 1 ~ Options & Analysis
  Scope: Analysis to determine best option for Citizens Bank to assume support for Appworks
  from Anovaa in order to support business requirements to retrieve documents and data
  for audit, regulatory and asset sale inquires
  Target Timeline: 8 – 12 Weeks
  Options Under Consideration
    Migration of Data + Creation of Basic Queryable Interface (AWS/On Prem)
    Lift & Shift of Underwriting Application(?) & Data to AWS/CFG On Prem
    CFG Support of Appworks as-is at Sungard
    Other: Hybrid
  Feature Prioritization & Sequencing
Phase 2 ~ Execute Option
  Scope: Execute Selected Option from Phase 1
  Target Timeline: 3 – 6 Months based assuming Option 1 Selected
Phase 3 ~ Decommission of Sungard
  Scope: Decommission of Sungard Hardware
  Target Timeline: 6- 8 Weeks
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters

## Slide 6
Phase 0: Prerequisites
  Anovaa Alignment
    IP Ownership Resolution w/Agreement for Citizens to Access Source Code
    Transition Agreement to include Anovaa and possibly Sungard
      Roles/Responsibilities
      Vendor SOW Expectations
  Initiative
    Scope Definition (Business Needs Assessment)
      High Level Definition
        Bring data/documents in-house
        R/O Queryable Interface to Data
        Ingest any loans with disbursements in 2022 into LaaS
        Any multi-year loan with an open credit converted into LaaS
    Funding source via Planview
  Team Formation
    Establish initial assessment team
      CB Tech Lead (completed – Eric)
      Secure former Entech SME’s as a consultant (complete – Sivarm)
      TS Resource Roles Identified
        Scrum Master (Vishal to obtain)
        Cloud/Application Architect (Vishal to obtain)
        Domain Analyst (Eric to obtain or push to Vishal)
        EDM/EDS
          Data Modeler (Eric to obtain)
          DBA (Eric to obtain)
        Senior Software Engineers
          Senior Full stack Lead Engineer (Vishal to obtain)
          Senior Engineer (Swami)
        Network Engineers
    Create JIRA Board
    Create Epics
    Establish Standup
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters

## Slide 7
Phase 1: Options & Analysis
  In order to select the best option to support the business needs TS will need to complete an Options & Analysis which will include an application assessment.
  Target Date:
    March 2021 latest; Optimal February 2021
  Options Under Consideration
    Migration of Data + Creation of Basic Queryable Interface (AWS/On Prem)
    Lift & Shift of Lender Web Application & Data to AWS/CFG On Prem
    CFG Support of Appworks as-is at Sungard
    Other: Hybrid
  Critical Success Factors
    Timely Response times and accessibly to Anovaa SMEs
    Ability to access required information only
    Quickly spin up a dedicated POD
  Limitations
    Feature Freeze
    Access only to data via the “Underwriting” application. No support for rate quotes, 3rd party interface, application processing, originations, servicing, etc
  Risks
    Limited number of Anovaa SMEs
    Appworks is a legacy system with inherent problems which Anovaa has had issues supporting
    All infrastructure is not based on CFG images nor standards
    Citizens currently has no expertise to support:
      Barracuda Load Balancers
      VEEAM Backup Software
    Underwriting website has never been scanned for Top 10 OWASP vulnerabilities
    1 Systematic Configuration Discovery if possible
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters

## Slide 8
Phase 1: Options & Analysis
  Application Assessment
    Data
      Define Data Sources & DB Versions
      Obtain ERDs
      Determine source locations for document retrieval
    Application
      Primary Functional Areas
      Technology Stack
        .net frameworks, VS Version, 3rd party libraries/controls, etc
      Security
      Encryption
      Methods for document retrieval
      Deployment Tiers
      Server OS Versions
      IIS Settings
      Systematic Configuration Discovery1 if possible
    Output
      System Documentation from Vendor*
      Source Code from Vendor* (Application, DB, system configurations)
      Current System Architecture and Topology
        Infrastructure / Network Diagrams
    1 Systematic Configuration Discovery if possible
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters

## Slide 9
Phase 2: Execute Option
  Phase 2 will implement the option recommended from Phase 1.
  Target Date:
    December 2021 latest; Optimal September 2021
  Critical Success Factors
    Operational solution before end of Anovaa support agreement
  Solution Architecture
  Agile Solution Execution
    To include incremental roll out of solution
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters

## Slide 10
Phase 3: Decommission Sungard
  This phase will implement the option recommended in Phase 1.
  Target Date:
    December 2021 latest; Optimal September 2021
  Critical Success Factors
    Archival of old AppWorks code/schema/data
    Decomission of AppWorks
    Disposal of hardware
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters

## Slide 11
Current Application Documentation
Link: HighLevelApplicationBlocks (citizensbank.com)
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters

## Slide 12
Current Application Documentation
Link: Entech_Assesment (citizensbank.com)
  Student/PERL Conceptual Design
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters

## Slide 13
Current Application Documentation
Link: Physical Network Diagram (citizensbank.com)
  * Dated 2017
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters

## Slide 14
Current Application Documentation
Link: EntechProjectWorkFlow (citizensbank.com)
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters

## Slide 15
Tech Team Stakeholders
  Support: Jeff Brock
  Wintel: Jon Dixon
  Network: Steve White
  Storage: Chino Rao
  EDS Architecture: Jim Gregg
  EDS: Karen Miglietta
  IAM: Ginny Palmer/Kevin Schwab
  DRET : Bob Stebbins/Matthew Russell
  Cyber: Matt Darlage
  IAM: Ginny Palmer/Kevin Schwab
  DRET : Bob Stebbins/Matthew Russell
  Cyber: TBD
  EDS Architecture: Jim Gregg
  Exchange: TBD
  Unix: TBD
  Barracuda Load Balancer: TBD
  Compliance/Risk: TBD
  Sungard: TBD
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters

## Slide 16
NEXT STEPS
  Enter Phase 0
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters

## Slide 17
Appendices: Migration
  Migration Execution Architectural Review Board
    Initial Setup / Prep
      DNS
      Port Opening
      Active Directory (Admin and RDP)
      Identity and Access Management / Security Groups
      Code Repository (BitBucket)
      CI/CD (Application Deployment Pipeline to include Infrastructure as Code )
      Disaster Recovery Strategy
      Data Migration Strategy
      Application Load Balancing
      SSL Certificate Definition (Venafi)
      Key Management (KMS)
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters

## Slide 18
Appendices: Migration
  Migration Execution Architectural Review Board
    Initial Setup / Prep
      DNS
      Port Opening
  Active Directory (AdmMigration Execution continued
    P-2 Deployment
      Deployment via IAC and CI/CD
      Testing (Infra, Security, Performance, Functional)
    P-1 Deployment
      Deployment via IAC and CI/CD
      Testing (Infra, Security, Performance, Functional)
    Change Advisory Board
    Production Deployment
      Deployment via IAC and CI/CD
      Data Migration
      Testing (Infra, Security, Performance, Functional, Parallel?)
    Decommission of old Sungard solution
      in and RDP)
      Identity and Access Management / Security Groups
      Code Repository (BitBucket)
      CI/CD (Application Deployment Pipeline to include Infrastructure as Code )
      Disaster Recovery Strategy
      Data Migration Strategy
      Application Load Balancing
      SSL Certificate Definition (Venafi)
      Key Management (KMS)
Notes: Performance. Inherently slow…
specifically the work queue for processors / underwriters